## Sheet1
|  |  |  | LEGEND: | [5 empty] | ONGOING (Coding, testing, registration & installation process) | [10 empty] | TRAINING
DRS GANTT CHART OF PENDING MODULES/SYSTEMS | [9 empty] | REVIEW | [10 empty] | PENDING
FOR IMPLEMENTATION
MODULES/TASKS | IN-CHARGE | F E B R U A R Y 2 0 2 3 | [19 empty] | M A R C H 2 0 2 3 | [22 empty] | A P R I L 2 0 2 3
|  | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31
DISPLAY RENTAL SYSTEM | GEDYM MAE SAB
ADMIN Access (MASTERFILE)
-Account Setup | bar: F E B R U A R Y 2 0 2 3 1 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to M A R C H 2 0 2 3 10
-Location Setup | bar: F E B R U A R Y 2 0 2 3 1 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to M A R C H 2 0 2 3 10
-Departments Setup | bar: F E B R U A R Y 2 0 2 3 1 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to M A R C H 2 0 2 3 10
-Display Category | bar: F E B R U A R Y 2 0 2 3 1 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to M A R C H 2 0 2 3 10
-Display Type Setup | bar: F E B R U A R Y 2 0 2 3 1 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to M A R C H 2 0 2 3 10
-Business Unit | bar: F E B R U A R Y 2 0 2 3 1 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to M A R C H 2 0 2 3 10
Planogram Merchandising (STORE IN-CHARGE ACCESS)
- Location Mapping | bar: F E B R U A R Y 2 0 2 3 24 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 19
Rental Management (AR Clerk, AP Clerk and Store Accounting IN-CHARGE ACCESS)
-Supplier Setup | bar: F E B R U A R Y 2 0 2 3 1 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 14
-Contract | bar: F E B R U A R Y 2 0 2 3 1 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 14
-Amortization Schedule | bar: F E B R U A R Y 2 0 2 3 17 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 14
-Debit/Credit Setup | bar: F E B R U A R Y 2 0 2 3 17 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 14
-Statement of Accounts | bar: F E B R U A R Y 2 0 2 3 17 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 14
-Adjustment | bar: F E B R U A R Y 2 0 2 3 17 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 14
-Payments | bar: F E B R U A R Y 2 0 2 3 17 to M A R C H 2 0 2 3 6; M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 14
Reports
-Payment History | bar: M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 19
-Adjustment History | bar: M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 19
-Suppliers Ledger | bar: M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 19
-Contract Report | bar: M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 19
-Audited Payment | bar: M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 19
-SOA Report | bar: M A R C H 2 0 2 3 9 to A P R I L 2 0 2 3 19
Prepared by: | Noted by: | F E B R U A R Y 2 0 2 3 23: Approved by:
DANNA MAE BANDA |  | F E B R U A R Y 2 0 2 3 1: Maria Cristina Evarle; F E B R U A R Y 2 0 2 3 24: Maria Neliza Fuertes CPA, CIA, CSCU, CISA, REB, CICA, CrFA, REA, REC
System Analyst II |  | F E B R U A R Y 2 0 2 3 1: Jr. Supervisor - IT SysDev; F E B R U A R Y 2 0 2 3 24: IAD Manager & Compliance Officer

## Sheet2
rqerwftwe
|  | rfqwewfw | wrw
wrfww
fweww